# Course: EGN4950C

# Group 12

# Civil Issue Matchmaker-Work Breakdown Structure (WBS)

# Authors: Davian Brooks, Michael Anstett, Tariq Khan, Andre Walia, David Landivar

Duration: August to December

| WBS Code | Task Name | Description | Responsible Party | Start Date | Due Date | Duration | Dependencies |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 | 1.1 Teams Planner & Agile Board Setup | Configure MS Teams Planner board, buckets, sprint cadence, task cards, and team notification rules. | Davian Brooks | 08/24/2026 | 08/28/2026 | 0.5 Week | None |
| 1.2 | 1.2 SDD/SRS Baseline & Tech Stack Review | Review SRS v1.0 and SDD v1.0 specifications; finalize repo layout, API contracts, and database schema conventions. | Davian Brooks | 08/24/2026 | 09/04/2026 | 2 Weeks | 1.1 |
| 1.3 | 1.3 CI/CD Pipeline & Dev Server Setup | Establish automated CI build runner, linter checks, containerized database containers, and staging deployment server. | David Landivar | 08/31/2026 | 09/11/2026 | 2 Weeks | 1.1 |
| 1.4 | 1.4 Progress Tracking & Risk Management | Monitor bi-weekly sprint velocity, track blockers on Teams Planner, manage architectural updates, and update audit logs. | Davian Brooks | 08/24/2026 | 12/11/2026 | 16 Weeks | 1.0 |
| M1 | M1: Dev Infrastructure & Planner Operational | MILESTONE: Teams Planner board configured, CI/CD pipeline operational, baseline architecture verified, dev environment ready. | Davian Brooks | 09/11/2026 | 09/11/2026 | - | 1.1, 1.2, 1.3 |
| 2.1 | 2.1 Repository Connector Base Interface | Implement abstract adapter interface for external task sources isolating rate limits and auth headers. | Andre Walia | 09/07/2026 | 09/18/2026 | 2 Weeks | 1.3 |
| 2.2 | 2.2 GitHub REST/GraphQL Adapter | Build concrete adapter for GitHub Civic Repositories / Code for America issue finder APIs. | David Landivar | 09/14/2026 | 09/25/2026 | 2 Weeks | 2.1 |
| 2.3 | 2.3 Secondary Repository Adapter (GitLab) | Develop a secondary adapter for GitLab civic projects to prove multi-source repository portability. | David Landivar | 09/21/2026 | 10/02/2026 | 2 Weeks | 2.1 |
| 2.4 | 2.4 Task Aggregation & Canonical Storage Engine | Extract and map source tasks into local canonical Task records (title, description, source URL, skills, effort). | Andre Walia | 09/21/2026 | 10/09/2026 | 3 Weeks | 2.2 |
| 2.5 | 2.5 Scheduled Scan Worker & State Tracker | Build automated background cron worker scanning enabled sources every 60 mins and detect open/closed tasks. | Andre Walia | 09/28/2026 | 10/09/2026 | 2 Weeks | 2.4 |
| 2.6 | 2.6 Source Outage Fault Tolerance & Diagnostics | Ensure failed scans to preserve last successful cached task data without corruption and log diagnostics. | Andre Walia | 10/05/2026 | 10/16/2026 | 2 Weeks | 2.5 |
| M2 | M2: Data Aggregation Pipeline Live | MILESTONE: Repository adapters successfully scraping, mapping, and storing task metadata from GitHub/GitLab on a 60-min interval. | Andre Walia | 10/16/2026 | 10/16/2026 | - | 2.5, 2.6 |
| 3.1 | 3.1 Database Schema & Relational Migrations | Design and implement SQL tables for Users, Repositories, Tasks, Recommendations, Claims, Feedback, and Audit logs. | Michael Anstett | 09/14/2026 | 09/25/2026 | 2 Weeks | 1.3 |
| 3.2 | 3.2 User Identity & Authentication Service | Implement registration, login, session tokens, and password hashing using Bcrypt/Argon2 salted representation. | David Landivar | 09/21/2026 | 10/02/2026 | 2 Weeks | 3.1 |
| 3.3 | 3.3 Volunteer Profile Management Engine | Build CRUD operations for volunteer profiles including skills, experience level, interest topics, and weekly availability. | Michael Anstett | 09/28/2026 | 10/09/2026 | 2 Weeks | 3.2 |
| 3.4 | 3.4 RBAC Authorization & Session Inactivity Timeout | Implement role enforcement (Volunteer, Maintainer, Admin) and automated 30-minute session inactivity expiration. | Michael Anstett | 10/05/2026 | 10/16/2026 | 2 Weeks | 3.2 |
| 3.5 | 3.5 Privacy Compliance, Export & Account Deletion | Develop permanent account deletion workflow, data anonymization engine, and machine-readable JSON data export. | Michael Anstett | 10/12/2026 | 10/23/2026 | 2 Weeks | 3.3 |
| M3 | M3: Auth & Volunteer Profiles Baseline | MILESTONE: Secure authentication, role enforcement, profile CRUD operations, session management, and privacy compliance verified. | Michael Anstett | 10/23/2026 | 10/23/2026 | - | 3.4, 3.5 |
| 4.1 | 4.1 Matching Engine Framework & Architecture | Establish modular matching service architecture, separating profile extraction, task filtering, and scoring calculations. | Michael Anstett | 09/28/2026 | 10/16/2026 | 3 Weeks | 2.4, 3.3 |
| 4.2 | 4.2 Weighted Multi-Factor Scoring Algorithm | Implement 0-100 compatibility formula: Skills (35%), Interests (20%), Experience (15%), Effort (15%), Location (5%), History (10%). | Michael Anstett | 10/12/2026 | 10/23/2026 | 2 Weeks | 4.1 |
| 4.3 | 4.3 Plain-Language Explanation Generator | Generate dynamic human-readable explanation strings identifying top positive and negative match factors for each task. | Michael Anstett | 10/19/2026 | 10/30/2026 | 2 Weeks | 4.2 |
| 4.4 | 4.4 Recommendation Filtering & Exclusions Engine | Build multi-criteria search filters (repo, topic, difficulty, effort, skill) and exclude closed or claimed tasks from feed. | Michael Anstett | 10/26/2026 | 11/06/2026 | 2 Weeks | 4.3 |
| M4 | M4: Matching Engine & Recommendation Live | MILESTONE: Recommendation engine generating ranked task feeds with compatibility scores, explanations, and filtering live in API. | Michael Anstett | 11/06/2026 | 11/06/2026 | - | 4.3, 4.4 |
| 5.1 | 5.1 Participation State Machine Service | Manage task participation states (Saved, Claimed, In Progress, Released, Completed) with chronological event logging. | Davian Brooks | 10/12/2026 | 10/23/2026 | 2 Weeks | 3.2, 2.4 |
| 5.2 | 5.2 Atomic Task Claim Concurrency Control Engine | Implement database transactions and active-claim unique constraints to prevent double claims by concurrent volunteers. | Davian Brooks | 10/19/2026 | 10/30/2026 | 2 Weeks | 5.1 |
| 5.3 | 5.3 Relevance Feedback & Bounded Learning Engine | Capture relevant/not relevant ratings with text explanations (up to 1,000 chars) and feed history into matching adjustments. | Davian Brooks | 10/26/2026 | 11/06/2026 | 2 Weeks | 5.1 |
| 5.4 | 5.4 Notification Event Engine & In-App Alerts | Create notification events for newly matching tasks and maintainer alerts when tasks are claimed, complete with delivery logs. | Davian Brooks | 11/02/2026 | 11/13/2026 | 2 Weeks | 5.1 |
| M5 | M5: Participation & Notifications Operational | MILESTONE: Atomic claim engine, state transitions, explicit feedback collection, and automated in-app/email notifications verified. | Davian Brooks | 11/13/2026 | 11/13/2026 | - | 5.2, 5.4 |
| 6.1 | 6.1 Maintainer Metadata Correction Overlay Service | Allow authorized maintainers to review/correct task tags, difficulty, and skills while preserving original source data. | Andre Walia | 10/26/2026 | 11/06/2026 | 2 Weeks | 2.4, 3.4 |
| 6.2 | 6.2 System Administration & Source Config | Build an admin interface to add, disable, or adjust scan intervals for repository sources without redeploying code. | Andre Walia | 11/02/2026 | 11/13/2026 | 2 Weeks | 2.1, 3.4 |
| 6.3 | 6.3 System Health Monitor & Audit Logging Service | Capture operational logs, failed scan metrics, privileged role changes, and auth failures without exposing secrets. | Andre Walia | 11/09/2026 | 11/20/2026 | 2 Weeks | 6.2 |
| 7.1 | 7.1 Responsive Client App Shell & Design System | Create a responsive layout shell supporting 360px to 1920px viewports with horizontal scrolling. | Tariq Khan | 10/05/2026 | 10/16/2026 | 2 Weeks | 1.3 |
| 7.2 | 7.2 Volunteer Dashboard & Profile Forms UI | Implement profile editor with adjacent validation messaging and form state preservation on validation failure. | Tariq Khan | 10/12/2026 | 10/23/2026 | 2 Weeks | 7.1, 3.3 |
| 7.3 | 7.3 Recommendation Feed, Task Details & Source Links | Build task recommendation feed displaying title, repo, compatibility score, explanation factors, and authoritative source links. | Tariq Khan | 10/26/2026 | 11/06/2026 | 2 Weeks | 7.1, 4.4 |
| 7.4 | 7.4 Maintainer Workspace & Admin Console UI | Build views for repository maintainers to submit task corrections and system administrators to manage sources and logs. | Tariq Khan | 11/02/2026 | 11/13/2026 | 2 Weeks | 7.1, 6.1 |
| 7.5 | 7.5 WCAG 2.1 AA Accessibility & Keyboard Nav | Implement visible focus rings, ARIA labels, semantic markup, and full keyboard control across all core workflows. | Tariq Khan | 11/09/2026 | 11/20/2026 | 2 Weeks | 7.3, 7.4 |
| M6 | M6: Full Application Frontend UI Baseline | MILESTONE: Responsive UI complete across desktop/mobile viewports; full frontend integrated with backend APIs and WCAG compliant. | Tariq Khan | 11/20/2026 | 11/20/2026 | - | 7.3, 7.4, 7.5 |
| 8.1 | 8.1 Automated Test Suite (Unit & Integration) | Develop unit tests for matching algorithms and integration tests for repository aggregation and claim state transitions. | Andre Walia | 11/09/2026 | 11/20/2026 | 2 Weeks | M4, M5 |
| 8.2 | 8.2 Performance & Load Testing Verification | Verify PR-1 (<5s recommendation latency @ 100 users), PR-2 (<3s profile latency), PR-3 (500 sessions), and PR-4 (50 repos/100k records). | David Landivar | 11/16/2026 | 11/27/2026 | 2 Weeks | 8.1 |
| 8.3 | 8.3 Security Audit, RBAC & Privacy Testing | Verify password hash security, HTTPS transport, secret masking, RBAC isolation, session expiration, and profile privacy. | David Landivar | 11/23/2026 | 12/04/2026 | 2 Weeks | 8.1 |
| 8.4 | 8.4 First-Time Volunteer Usability Trial | Execute formal usability trial with representative users verifying >=80% complete onboarding & claim within 5 mins. | David Landivar | 11/23/2026 | 12/04/2026 | 2 Weeks | M6 |
| M7 | M7: QA Verification & Security Audit Complete | MILESTONE: All SRS performance benchmarks (PR-1 to PR-5), security rules (SP-1 to SP-7), and usability targets (US-1) formally passed. | David Landivar | 12/04/2026 | 12/04/2026 | - | 8.2, 8.3, 8.4 |
| 9.1 | 9.1 Production Cloud Deployment & Backups | Deploy application to production host, configure SSL certificates, set up automated 24-hr DB backup retention. | David Landivar | 11/23/2026 | 12/04/2026 | 2 Weeks | M7 |
| 9.2 | 9.2 Final Software Documentation & User Manuals | Compile complete technical documentation, developer API references, maintainer user guides, and final report. | Davian Brooks | 12/01/2026 | 12/08/2026 | 1 Week | 9.1 |
| 9.3 | 9.3 Senior Design II Presentation & Demo | Prepare final presentation slides, conduct live product demonstrations for course instructors/sponsors, and deliver final code repo. | Davian Brooks | 12/07/2026 | 12/11/2026 | 1 Week | 9.2 |
| M8 | M8: Final Senior Design II Project Handover | MILESTONE: Successful final presentation, live system deployed in production, documentation handed over, course completion achieved. | Davian Brooks | 12/11/2026 | 12/11/2026 | - | 9.3 |

**Note: Assignments and Due dates are subject to change

Team Member Task Allocation & Responsibilities

1. Davian Brooks (Project Manager & Frontend Lead)

- Primary Responsibilities: Overall project management, schedule tracking on Teams Planner, responsive UI architecture, WCAG 2.1 AA accessibility compliance, and final presentation lead.

- Key Deliverables:

  - Lead UI/UX design and implementation.

  - Administer usability testing with first-time volunteer participants.

  - Coordinate final report compilation and showcase presentation.

2. Michael Anstett (Backend & Security Lead)

- Primary Responsibilities: Application service coordination, authentication/authorization (RBAC), profile management services, and technical documentation.

- Key Deliverables:

  - Implement authentication, session handling, and RBAC.

  - Build volunteer profile and account deletion API.

  - Implement maintainer correction processing logic.

  - Lead technical documentation and API specification assembly.

3. Tariq Khan (Data & Repository Integration Lead)

- Primary Responsibilities: Relational database design, persistence layer, repository connector adapters, and automated task aggregation engine.

- Key Deliverables:

  - Design and implement relational database schema and migration scripts.

  - Develop external repository connector adapters for source integration.

  - Build hourly task aggregation and normalization engine.

  - Lead Data Pipeline Milestone.

4. Andre Walia (Algorithm & Matching Lead)

- Primary Responsibilities: Recommendation engine design, weighted compatibility scoring algorithm, explanation factor generator, and feedback loop integration.

- Key Deliverables:

  - Build multi-factor compatibility scoring engine.

  - Implement human-readable explanation generator and filter/sort APIs.

  - Integrate volunteer relevance feedback and history learning loop.

  - Lead Recommendation Integration Milestone.

5. David Landivar (Systems, QA, & Infrastructure Lead)

- Primary Responsibilities: DevOps/CI-CD, concurrency control, notification service, production deployment, and system verification/testing.

- Key Deliverables:

  - Setup developer environment, Docker, and CI/CD deployment pipelines.

  - Implement atomic task claiming concurrency protection.

  - Build event-driven notification manager service.

  - Lead automated performance/load testing and production backup setup.

Key Project Milestones Summary

Milestone 1 (M1) – Aggregation & Data Pipeline Operational (Oct 09, 2026)

Criteria: Automated background scanner successfully fetches, normalizes, and stores tasks from external repositories with metadata preserved.

Milestone 2 (M2) – Recommendation Engine Integrated (Oct 23, 2026)

Criteria: Matching algorithm successfully computes compatibility scores and generates multi-factor explanations for volunteer profiles.

Milestone 3 (M3) – Full System Integration Completed (Nov 13, 2026)

Criteria: Responsive frontend interface fully connected to application services, enabling end-to-end user workflows from account registration to task claiming.

Milestone 4 (M4) – System Verification Passed (Nov 27, 2026)

Criteria: System passes all latency (<5s), concurrency (100 active users), security, accessibility, and usability benchmarks specified in the SRS.

Milestone 5 (M5) – Final Deployment & Presentation Completed (Dec 11, 2026)

Criteria: Software successfully deployed to production environment with daily backups enabled; final report and presentation delivered.

**Note: Completion dates subject to change